## AION GO-LIVE Run Book
AION GO-Live Run Book
Task # | Tasks | Dates (TBD) | Duration | Assigned to | Action Item | Notes
1 | copy TST database to production, we need the structure and the data for the reference lists |  |  | DB Team | Done | Find out how long the DB team may think this will take.; Cherwell ticket
2 | production app in azure may need to be created by DevOps Team and pipeline set up , PROD isn't in the pipeline right now (11/22) | 2023-12-04 |  | DevOps Team | Done | ; Cherwell ticket
3 | create/set up production functions - DevOps Team to set this up |  |  | DevOps Team | Done | ; Cherwell ticket
4 | Update links inside Aion to production URLs - Accela, Reporting, Accela Deeplink |  |  | AION Team | Done
5 | update web.config for production environment |  |  | AION Team | Done
6 | remove debug table/link/tab from admin screen |  |  | AION Team | Done
7 | Keyvault connection strings for prd from EA Team |  |  | EA Team | Done | need to meet and find out more info or steps from EA Team; Cherwell ticket
8 | Add Keyvault connection strings for prd from EA Team to web.config |  |  | AION Team | Done
9 | Mandatory email recipient list - leave as just QA and Team - need to check for when to turn on emails after post go live validation happens. |  |  | AION Team | Done (left blank)
10 | LoggingServiceBusConnectionString in web.config changed to PROD instance |  |  | AION Team | Done
11 | Landing page text - need business input on this |  |  | AION Team/Business | Done | Need current text from Business
12 | Change links for PROD reports for the reports page |  |  | AION Team | Done (via coordination with Jeffrey Chen)
13 | Push code to PROD using pipeline | 2023-12-04 |  | AION Team | Done
14 | Database configuration - keyvault connection string access is working |  |  | AION/DB Team |  | ; Cherwell ticket
15 | Migration - Load current users |  |  | AION Team/Business |  | Run Carlos's code or pull from TST? Needs business input - may be needed to add manually
16 | Add users from outside the county for calendar placement, add as city users, need to have the permitplanreview calendar id and set up sub-calendars |  |  | AION Team/Business |  | AION Team add the calendars, users that are city users need to be added by the business - pull from tst maybe?
17 | users need to be assigned roles |  |  | AION Team/Business
18 | express configuration setup - needs to be done before migrating express reservations and running express function |  |  | AION Team/Business
19 | Business may need to create the reservations in EPM then migrate them. Business needs to decide whether to do this or just let the express engine function run and then clean up the result |  |  | Business
20 | Migration - Express reservations migrated |  |  |  |  | Any NPAs or Express Res or Schedules done after migration is completed may habe to be added. Depends on migration timing.
21 | Run Express reservation engine function - would only need for time frame in future past migrated existing reservations - up to six month time frame |  |  | AION Team
22 | Add Holidays - can we migrate these or does the business need to add? |  |  |  |  | Migration or pull from TST? Business should decide which. Manually add by business.
23 | Set up access for SSRS reports - move reports to PROD servers, set up subscriptions for PROD probably can be migrated by Jeffrey and updated to PROD settings |  |  | Jeffrey | Done
24 | Migration - Existing NPAs migrated, may need business help on this |  |  |  |  | Any NPAs or Express Res or Schedules done after migration is completed may habe to be added. Depends on migration timing.
25 | AION Admin configurations - tabs settings |  |  | AION Team/Business
26 | Set up remaining meeting rooms to be assigned |  |  | Janessa |  | add to db table for the meeting rooms
27 | set up public landing page in azure - currently landing page is not public |  |  | DevOps | Done | ; Cherwell ticket
28 | determine what QA users need to be added to sus_aion_users_prd |  |  | QA/Business
29 | determine the sus_aion_users_prd list |  |  | Business | Done
30 | set up sus_aion_users_prd in Azure - EA Team |  |  | IAM - Sean Gray | In process | meet with EA Team to find out what steps are needed; Cherwell ticket
31 | determine the sus_aion_external_users_prd users list |  |  | Business | N/A
32 | set up sus_aion_external_users_prd with external users in Azure - EA Team |  |  | IAM - Sean Gray | Only if external users | meet with EA Team to find out what steps are needed; Cherwell ticket
33 | Business send out communication to Business that rogue emails may occur. |  |  | Business
34 | FIFO projects - optimizer - runs after migration to validate |  |  | N/A | N/A | Tested when the FIFO projects are created to make sure it's working.
35 | Verify Accela connections - Dummy project?? Test of some kind |  |  | QA/AION Team | Pre Go-Live validation
36 | SSRS Data validation of converted data |  |  | N/A | N/A
37 | Migration - Data validation of migrated PROD data |  |  | N/A | N/A
38 | Verify Email Engine is turned on in PROD |  |  | AION Team
39 | Set up internal Teams Channel
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54