## Sheet1
Project: | LUE FY19 EPM Replacement | [12 empty] | Customer Experience Time | Filled
[14 empty] | Money | Concern
Business Analyst: | Nate Olson | Sara Fisher | 2/11/18 - 2/22/18 | [10 empty] | Resource | Risk
Time
Req# | Area | Process | Gap to be analyzed/question to be answered | Description | Severity | Responsible | Target Date | Status | Workaround | Impact | Action | Note | GAP Result
LUE-31 | Land Development | Access System | Email opt in or outAs a customer | As a customer I want to opt into or out of email notifications So that I can choose to look at the dashboard for information or emails |  | Nate Olson
LUE-37 | Land Development | Access System | Autofill Company nameAs a Customer | As a CustomerI want to use autofill functionality when I an typing in the company name during profile creation So that I can add the correct company to my profile. |  | Nate Olson
LUE-162 | Land Development | LD Intake | Answer questionsAs a Customer | As a Customer I want to be able to answer questions the intake coordinator has on the application from the system. So that I can be notified and respond |  | Nate Olson
LUE-165 | Land Development | LD Intake | BUSINESS: Address Verification As a GIS Address Staff | As a GIS Address Staff I want to perform the address verification in the system So that we can remove the paper process and streamline this for the customer. |  | Nate Olson
LUE-173 | Land Development | LD Intake | Dashboard view of fees not paidAs a LD Customer | As a LD Customer I want a dashboard notification if I have not paid for the fees within 48 hours (2 business days) So that I can see the project that hasn't been paid for and pay for the fees. |  | Nate Olson | [5 empty] | bla bla bla
LUE-175 | Land Development | LD Intake | Edit applicationAs a LD Intake Coordinator | As a LD Intake Coordinator I want to be able to edit all fields on the customer application/project as necessary So that this key information can be updated as required. |  | Nate Olson
LUE-183 | Land Development | LD Intake | Lock customer application edit during reviewAs a LD Intake Coordinator | As a LD Intake Coordinator I do not want the customer to be able to edit their application if either the town or the county has rejected the application and both the town and the county has reviewed the submittal and dispositioned the application. So that the customer cannot make changes to the application in the middle of a review cycle. |  | Nate Olson
LUE-188 | Land Development | LD Intake | Internal 48 hour notificationAs a LD Intake Coordinator | As a LD Intake Coordinator I want to be notified if the application has not been accepted or rejected by both the county and the town (as applicable) within 48 business hours (2 business days) So that I know to take action for not meeting the goal |  | Nate Olson
LUE-189 | Land Development | LD Intake | Every 7 days notification not acceptedAs a LD Intake Coordinator | As a LD Intake Coordinator I want to be notified if the application has not been accepted or rejected by both the county and the town (as applicable every 7 days So that I know to take action for not meeting the goal |  | Nate Olson
LUE-197 | Land Development | LD Intake | Customer response notificationAs a LD Intake Coordinator | As a LD Intake Coordinator I want to be notified on the dashboard when a customer has responded to my question. So that I am aware of the response. |  | Nate Olson
LUE-198 | Land Development | LD Intake | Disposition expedited request As a LD Intake Coordinator | As a LD Intake Coordinator I want to be able to approve or reject the customers request for an expedited review So that they can be made aware of the LD decision on the request. |  | Nate Olson
LUE-203 | Land Development | LD Intake | Internal 48 hour notificationAs a LD Manager | As a LD Manager I want to be notified if the application has not been accepted or rejected within 48 business hours (2 business days) So that I know to take action for not meeting the goal |  | Nate Olson
LUE-211 | Land Development | LD Post Intake Revision | Request a change As a customer | As a customer I want to request a revision to a submitted plan after intake but before plan review has been completed So that I change the project and have it reviewed. |  | Nate Olson
LUE-214 | Land Development | LD Post Intake Revision | Request revision post intake approvalAs a customer | As a customer I want to request approval to submit a small revision to plans after intake approval has taken place. So that small revisions can be included in the current cycle of review |  | Nate Olson
LUE-215 | Land Development | LD Post Intake Revision | Request a changeAs a LD Intake Coordinator | As a LD Intake Coordinator I want the customer to request a change from me prior to being able to submit the change to the project So that we can validate what the customer will need to do to submit the change. |  | Nate Olson
LUE-219 | Land Development | LD Post Intake Revision | BUSINESS DECISION GAP: Reset 21 day timer after intake for small revisionAs a plan reviewer | As a plan reviewer I want the time calculation to reset after intake has been approved for small revision post intake approval So that we have a new 21 days to review the plans |  | Nate Olson
LUE-222 | Land Development | Finance | Approve refund As a LD Manager | As a LD ManagerI want the ability to approve a refund to the customerSo that they are credited back when overcharged. |  | Nate Olson
LUE-240 | Land Development | LD as Built | Plan review for as builtAs a plan reviewer | As a plan reviewer I want complete the plan review process for an as built application So that we can compare the as built to the plans |  | Nate Olson
LUE-278 | Land Development | LD Bonds | Electronic seal for bond estimateAs a LD Customer | As a LD Customer I want to provide an electronic seal to the bond estimate So that that the information is sealed and verified |  | Nate Olson
LUE-292 | Land Development | LD Bonds | Calendar invite for bonds estimateAs a NC DOT Inspector | As a NC DOT Inspector I want a calendar appointment sent to me when I need to do an inspection So that I can schedule the inspection on my calendar |  | Nate Olson
LUE-296 | Land Development | LD Bonds | Calendar invite for bonds estimateAs a town inspector | As a town inspector I want a calendar appointment sent to me when I need to do an inspection So that I can schedule the inspection on my calendar |  | Nate Olson
LUE-308 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-309 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a LD Inspector | As a LD Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-310 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a Zoning Inspector | As a Zoning Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-328 | Land Development | LD Precon Meeting | Schedule Precon Inspection meetingAs a Erosion control Inspector | As a Erosion control Inspector I want the Owner/developer to be able to schedule the preconstruction inspection meeting via the system. So that this can be scheduled systemically and reduce manual interaction |  | Nate Olson
LUE-330 | Land Development | LD Precon Meeting | Manually add attendees to precon inspection meetingAs a owner/develop | As a owner/develop I want to be add attendees manually to the calendar invite for the preconstruction meeting So that I can add others to the meeting. |  | Nate Olson
LUE-331 | Land Development | LD Precon Meeting | Otion to manually contact erosion control inspectorAs a owner/develop | As a owner/develop I want to choose an option to contact the erosion control inspector if times needed are not available. So that I can schedule the preconstruction inspection meeting. |  | Nate Olson
LUE-332 | Land Development | LD Precon Meeting | Town designee invited to precon meetingAs a Town | As a Town I want to my designee to be invited to the precon meeting So that we can represent town interests in the meeting |  | Nate Olson
LUE-333 | Land Development | Notifications | Email optionAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to opt into or out of email notifications So that I can limit the amount of email I get. |  | Nate Olson
LUE-335 | Land Development | Notifications | Turn off secondary notifications As a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to turn notificaiton on and off for any secondary roles that I am assigned. So that I can choose to see those notificaiton as needed. |  | Nate Olson
LUE-338 | Land Development | Notifications | Dismiss notifications As a EPR User | As a EPR User I want to be able to dismiss the notifications that I receive So that I can clear them out after I have taken action. |  | Nate Olson
LUE-339 | Land Development | Notifications | View dismissed notifications As a EPR User | As a EPR User I want to be able to view the notifications that I have dismissed So that I can review prior notifications as necessary. |  | Nate Olson
LUE-340 | Land Development | Notifications | Notification routes to projectAs a EPR | As a EPR User I want to routed automatically to that particular project when I click on the notification. So that I easily navigate within the system. |  | Nate Olson
LUE-342 | Land Development | Overall | Dashboard viewAs a Customer | As a Customer I want a dashboard to view, monitor and manage my projects and status So that I can see my projects, statuses and process necessary steps. |  | Nate Olson
LUE-343 | Land Development | Overall | online chatAs a Customer | As a Customer I want to be able to perform an online chat for any questions that I have So that I can have questions answered in real time. |  | Nate Olson
LUE-344 | Land Development | Overall | Configure dashboard viewAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to make configurations to my dashboard view So that I can work with the system in a manner most efficient to me. |  | Nate Olson
LUE-345 | Land Development | Overall | Dashboard role/user viewAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to view other epr roles and users dashboards So that I can view that necessary information as necessary |  | Nate Olson
LUE-346 | Land Development | Overall | Remote view of customer screen As a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to view the customers screen as they use it So that I can help the customer use the system. |  | Nate Olson
LUE-348 | Land Development | Overall | Indicate OOO reassignmentAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to notate that I am OOO during a time frame So that I do not receive projects and choose who will receive my assignments |  | Nate Olson
LUE-351 | Land Development | Overall | Assign user to multiple rolesAs a EPR Manager | As a EPR Manager I want to be able to assign user to multiple roles So that I can perform those functions as needed. |  | Nate Olson
LUE-353 | Land Development | Overall | Autosave system entryAs a EPR User | As a EPR User I want the system to auto save data entered and attachments So that I don't have to continually remember to hit save. |  | Nate Olson
LUE-355 | Land Development | Overall | Auto correct text entryAs a EPR User | As a EPR User I want the system to auto correct text entry as is entered So that basic word corrections can be automatically done |  | Nate Olson
LUE-356 | Land Development | Overall | Export dashboardAs a EPR User | As a EPR User I want to be able to export my dashboard view to excel So that I can work with the data set outside the system |  | Nate Olson
LUE-358 | Land Development | Overall | Text EditorAs a EPR User | As a EPR User I want text editor to format my comments and communications. So that I can see the format going to the customer. |  | Nate Olson
LUE-360 | Land Development | Overall | Create additional dashboard informationAs a EPR User | As a EPR User I want to create my own additional dashboard information So that I have information readily accessible that I need |  | Nate Olson
LUE-363 | Land Development | Overall | Shadow roles As a LD Manager | As a LD Manager I want to be able to choose the user role I want to shadow so that I can see the functions and notifications of that role. So that I can work as a user in that role. |  | Nate Olson
LUE-364 | Land Development | Overall | Dashboard viewAs a Plan Reviewer | As a Plan Reviewer I want a dashboard to view, manage and complete work. So that I can see my work in one place. |  | Nate Olson
LUE-365 | Land Development | Scheduling Bonds | Schedule annual bond inspectionAs a Bonds Inspector | As a Bonds Inspector I want the system to schedule me for a minor annual inspection on each bonded project So that I can account for time |  | Nate Olson
LUE-366 | Land Development | Scheduling Bonds | As built calendar inviteAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection for the as built BMP So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-367 | Land Development | Scheduling Bonds | 3 year bond inspection inviteAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-368 | Land Development | Scheduling Bonds | 3 year bond inspection inviteAs a LD Inspector | As a LD Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-369 | Land Development | Scheduling Bonds | Change assinged inspectorAs a LD Manager | As a LD Manager I want to be able to change the inspector assigned to perform the inspection So that they can be adjusted as needed |  | Nate Olson
LUE-370 | Land Development | Scheduling Bonds | 3 year bond inspection calendar inviteAs a Zoning Inspector | As a Zoning Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-386 | Land Development | LD as Built | Plan review for as builtAs a plan reviewer | As a plan reviewer I want complete the plan review process for an as built application So that we can compare the as built to the plans |  | Nate Olson
LUE-424 | Land Development | LD Bonds | Electronic seal for bond estimateAs a LD Customer | As a LD Customer I want to provide an electronic seal to the bond estimate So that that the information is sealed and verified |  | Nate Olson
LUE-438 | Land Development | LD Bonds | Calendar invite for bonds estimateAs a NC DOT Inspector | As a NC DOT Inspector I want a calendar appointment sent to me when I need to do an inspection So that I can schedule the inspection on my calendar |  | Nate Olson
LUE-442 | Land Development | LD Bonds | Calendar invite for bonds estimateAs a town inspector | As a town inspector I want a calendar appointment sent to me when I need to do an inspection So that I can schedule the inspection on my calendar |  | Nate Olson
LUE-454 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-455 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a LD Inspector | As a LD Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-456 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a Zoning Inspector | As a Zoning Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-474 | Land Development | LD Precon Meeting | Schedule Precon Inspection meetingAs a Erosion control Inspector | As a Erosion control Inspector I want the Owner/developer to be able to schedule the preconstruction inspection meeting via the system. So that this can be scheduled systemically and reduce manual interaction |  | Nate Olson
LUE-476 | Land Development | LD Precon Meeting | Manually add attendees to precon inspection meetingAs a owner/develop | As a owner/develop I want to be add attendees manually to the calendar invite for the preconstruction meeting So that I can add others to the meeting. |  | Nate Olson
LUE-477 | Land Development | LD Precon Meeting | Otion to manually contact erosion control inspectorAs a owner/develop | As a owner/develop I want to choose an option to contact the erosion control inspector if times needed are not available. So that I can schedule the preconstruction inspection meeting. |  | Nate Olson
LUE-478 | Land Development | LD Precon Meeting | Town designee invited to precon meetingAs a Town | As a Town I want to my designee to be invited to the precon meeting So that we can represent town interests in the meeting |  | Nate Olson
LUE-479 | Land Development | Notifications | Email optionAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to opt into or out of email notifications So that I can limit the amount of email I get. |  | Nate Olson
LUE-481 | Land Development | Notifications | Turn off secondary notifications As a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to turn notificaiton on and off for any secondary roles that I am assigned. So that I can choose to see those notificaiton as needed. |  | Nate Olson
LUE-484 | Land Development | Notifications | Dismiss notifications As a EPR User | As a EPR User I want to be able to dismiss the notifications that I receive So that I can clear them out after I have taken action. |  | Nate Olson
LUE-485 | Land Development | Notifications | View dismissed notifications As a EPR User | As a EPR User I want to be able to view the notifications that I have dismissed So that I can review prior notifications as necessary. |  | Nate Olson
LUE-486 | Land Development | Notifications | Notification routes to projectAs a EPR User | As a EPR User I want to routed automatically to that particular project when I click on the notification. So that I easily navigate within the system. |  | Nate Olson
LUE-488 | Land Development | Overall | Dashboard viewAs a Customer | As a Customer I want a dashboard to view, monitor and manage my projects and status So that I can see my projects, statuses and process necessary steps. |  | Nate Olson
lue-489 | Land Development | Overall | online chatAs a Customer | As a Customer I want to be able to perform an online chat for any questions that I have So that I can have questions answered in real time. |  | Nate Olson
LUE-490 | Land Development | Overall | Configure dashboard viewAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to make configurations to my dashboard view So that I can work with the system in a manner most efficient to me. |  | Nate Olson
LUE-491 | Land Development | Overall | Dashboard role/user viewAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to view other epr roles and users dashboards So that I can view that necessary information as necessary |  | Nate Olson
LUE-492 | Land Development | Overall | Remote view of customer screen As a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to view the customers screen as they use it So that I can help the customer use the system. |  | Nate Olson
LUE-494 | Land Development | Overall | Indicate OOO reassignmentAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to notate that I am OOO during a time frame So that I do not receive projects and choose who will receive my assignments |  | Nate Olson
LUE-497 | Land Development | Overall | Assign user to multiple rolesAs a EPR Manager | As a EPR Manager I want to be able to assign user to multiple roles So that I can perform those functions as needed. |  | Nate Olson
LUE-499 | Land Development | Overall | Autosave system entryAs a EPR User | As a EPR User I want the system to auto save data entered and attachments So that I don't have to continually remember to hit save. |  | Nate Olson
LUE-501 | Land Development | Overall | Auto correct text entryAs a EPR User | As a EPR User I want the system to auto correct text entry as is entered So that basic word corrections can be automatically done |  | Nate Olson
LUE-502 | Land Development | Overall | Export dashboardAs a EPR User | As a EPR User I want to be able to export my dashboard view to excel So that I can work with the data set outside the system |  | Nate Olson
LUE-504 | Land Development | Overall | Text EditorAs a EPR User | As a EPR User I want text editor to format my comments and communications. So that I can see the format going to the customer. |  | Nate Olson
LUE-506 | Land Development | Overall | Create additional dashboard informationAs a EPR User | As a EPR User I want to create my own additional dashboard information So that I have information readily accessible that I need |  | Nate Olson
LUE-509 | Land Development | Overall | Shadow roles As a LD Manager | As a LD Manager I want to be able to choose the user role I want to shadow so that I can see the functions and notifications of that role. So that I can work as a user in that role. |  | Nate Olson
LUE-510 | Land Development | Overall | Dashboard viewAs a Plan Reviewer | As a Plan Reviewer I want a dashboard to view, manage and complete work. So that I can see my work in one place. |  | Nate Olson
LUE-511 | Land Development | Scheduling Bonds | Schedule annual bond inspectionAs a Bonds Inspector | As a Bonds Inspector I want the system to schedule me for a minor annual inspection on each bonded project So that I can account for time |  | Nate Olson
LUE-512 | Land Development | Scheduling Bonds | As built calendar inviteAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection for the as built BMP So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-513 | Land Development | Scheduling Bonds | 3 year bond inspection inviteAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-514 | Land Development | Scheduling Bonds | 3 year bond inspection inviteAs a LD Inspector | As a LD Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-515 | Land Development | Scheduling Bonds | Change assinged inspectorAs a LD Manager | As a LD Manager I want to be able to change the inspector assigned to perform the inspection So that they can be adjusted as needed |  | Nate Olson
LUE-516 | Land Development | Scheduling Bonds | 3 year bond inspection calendar inviteAs a Zoning Inspector | As a Zoning Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-531 | Land Development | LD as Built | Plan review for as builtAs a plan reviewer | As a plan reviewer I want complete the plan review process for an as built application So that we can compare the as built to the plans |  | Nate Olson
LUE-569 | Land Development | LD Bonds | Electronic seal for bond estimateAs a LD Customer | As a LD Customer I want to provide an electronic seal to the bond estimate So that that the information is sealed and verified |  | Nate Olson
LUE-583 | Land Development | LD Bonds | Calendar invite for bonds estimateAs a NC DOT Inspector | As a NC DOT Inspector I want a calendar appointment sent to me when I need to do an inspection So that I can schedule the inspection on my calendar |  | Nate Olson
LUE-587 | Land Development | LD Bonds | Calendar invite for bonds estimateAs a town inspector | As a town inspector I want a calendar appointment sent to me when I need to do an inspection So that I can schedule the inspection on my calendar |  | Nate Olson
LUE-599 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-600 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a LD Inspector | As a LD Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-601 | Land Development | LD Create Bonds | Calendar invite for bonds estimateAs a Zoning Inspector | As a Zoning Inspector I want a calendar invite sent to me complete an inspection to verify the bond estimate So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-619 | Land Development | LD Precon Meeting | Schedule Precon Inspection meetingAs a Erosion control Inspector | As a Erosion control Inspector I want the Owner/developer to be able to schedule the preconstruction inspection meeting via the system. So that this can be scheduled systemically and reduce manual interaction |  | Nate Olson
LUE-621 | Land Development | LD Precon Meeting | Manually add attendees to precon inspection meetingAs a owner/develop | As a owner/develop I want to be add attendees manually to the calendar invite for the preconstruction meeting So that I can add others to the meeting. |  | Nate Olson
LUE-622 | Land Development | LD Precon Meeting | Otion to manually contact erosion control inspectorAs a owner/develop | As a owner/develop I want to choose an option to contact the erosion control inspector if times needed are not available. So that I can schedule the preconstruction inspection meeting. |  | Nate Olson
LUE-623 | Land Development | LD Precon Meeting | Town designee invited to precon meetingAs a Town | As a Town I want to my designee to be invited to the precon meeting So that we can represent town interests in the meeting |  | Nate Olson
LUE-624 | Land Development | Notifications | Email optionAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to opt into or out of email notifications So that I can limit the amount of email I get. |  | Nate Olson
LUE-626 | Land Development | Notifications | Turn off secondary notifications As a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to turn notificaiton on and off for any secondary roles that I am assigned. So that I can choose to see those notificaiton as needed. |  | Nate Olson
LUE-629 | Land Development | Notifications | Dismiss notifications As a EPR User | As a EPR User I want to be able to dismiss the notifications that I receive So that I can clear them out after I have taken action. |  | Nate Olson
LUE-630 | Land Development | Notifications | View dismissed notifications As a EPR User | As a EPR User I want to be able to view the notifications that I have dismissed So that I can review prior notifications as necessary. |  | Nate Olson
LUE-631 | Land Development | Notifications | Notification routes to projectAs a EPR User | As a EPR User I want to routed automatically to that particular project when I click on the notification. So that I easily navigate within the system. |  | Nate Olson
LUE-633 | Land Development | Overall | Dashboard viewAs a Customer | As a Customer I want a dashboard to view, monitor and manage my projects and status So that I can see my projects, statuses and process necessary steps. |  | Nate Olson
LUE-634 | Land Development | Overall | online chatAs a Customer | As a Customer I want to be able to perform an online chat for any questions that I have So that I can have questions answered in real time. |  | Nate Olson
LUE-635 | Land Development | Overall | Configure dashboard viewAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to make configurations to my dashboard view So that I can work with the system in a manner most efficient to me. |  | Nate Olson
LUE-636 | Land Development | Overall | Dashboard role/user viewAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to view other epr roles and users dashboards So that I can view that necessary information as necessary |  | Nate Olson
LUE-637 | Land Development | Overall | Remote view of customer screen As a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to be able to view the customers screen as they use it So that I can help the customer use the system. |  | Nate Olson
LUE-639 | Land Development | Overall | Indicate OOO reassignmentAs a EPR business user (county/town employee) | As a EPR business user (county/town employee) I want to notate that I am OOO during a time frame So that I do not receive projects and choose who will receive my assignments |  | Nate Olson
LUE-642 | Land Development | Overall | Assign user to multiple rolesAs a EPR Manager | As a EPR Manager I want to be able to assign user to multiple roles So that I can perform those functions as needed. |  | Nate Olson
LUE-644 | Land Development | Overall | Autosave system entryAs a EPR User | As a EPR User I want the system to auto save data entered and attachments So that I don't have to continually remember to hit save. |  | Nate Olson
LUE-646 | Land Development | Overall | Auto correct text entryAs a EPR User | As a EPR User I want the system to auto correct text entry as is entered So that basic word corrections can be automatically done |  | Nate Olson
LUE-647 | Land Development | Overall | Export dashboardAs a EPR User | As a EPR User I want to be able to export my dashboard view to excel So that I can work with the data set outside the system |  | Nate Olson
LUE-649 | Land Development | Overall | Text EditorAs a EPR User | As a EPR User I want text editor to format my comments and communications. So that I can see the format going to the customer. |  | Nate Olson
LUE-651 | Land Development | Overall | Create additional dashboard informationAs a EPR User | As a EPR User I want to create my own additional dashboard information So that I have information readily accessible that I need |  | Nate Olson
LUE-654 | Land Development | Overall | Shadow roles As a LD Manager | As a LD Manager I want to be able to choose the user role I want to shadow so that I can see the functions and notifications of that role. So that I can work as a user in that role. |  | Nate Olson
LUE-655 | Land Development | Overall | Dashboard viewAs a Plan Reviewer | As a Plan Reviewer I want a dashboard to view, manage and complete work. So that I can see my work in one place. |  | Nate Olson
LUE-656 | Land Development | Scheduling Bonds | sending outlook calendar invite; Schedule annual bond inspectionAs a Bonds Inspector | As a Bonds Inspector I want the system to schedule me for a minor annual inspection on each bonded project So that I can account for time |  | Nate Olson
LUE-657 | Land Development | Scheduling Bonds | Sending outlook calendar invite;As built calendar inviteAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection for the as built BMP So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-658 | Land Development | Scheduling Bonds | 3 year bond inspection inviteAs a Erosion Control Inspector | As a Erosion Control Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-659 | Land Development | Scheduling Bonds | 3 year bond inspection inviteAs a LD Inspector | As a LD Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-660 | Land Development | Scheduling Bonds | Change assinged inspectorAs a LD Manager | As a LD Manager I want to be able to change the inspector assigned to perform the inspection So that they can be adjusted as needed |  | Nate Olson
LUE-661 | Land Development | Scheduling Bonds | 3 year bond inspection calendar inviteAs a Zoning Inspector | As a Zoning Inspector I want a calendar invite sent to me complete an inspection to verify the 3 year inspection So that manual steps to schedule the inspection are reduced |  | Nate Olson
LUE-670 | Land Development | Scheduling Bonds | CO Checklist electronic signatureAs a customer | As a customer I want to electronically sign the CO Checklist So that I can easily sign it and it will be on the project record |  | Nate Olson
LUE-672 | Land Development | Scheduling Bonds | Upload letters to projectAs a customer | As a customer I want to know what certification letters I need to obtain So that I can upload to them to the project to get my plans approved. |  | Nate Olson
LUE-676 | Land Development | Scheduling Bonds | Choose expedited on new cycles As a LD customer | As a LD customer I want to make a determination before each new review cycle if I want to utilize expedited review So that the standard process or expedited process can be utilized. |  | Nate Olson
LUE-690 | Land Development | Scheduling Bonds | Town Choice on when to send issues to the customerAs a LD manager | As a LD manager I want each town to choose how they want to send issues to the customer after a plan review has been completed. So that they can adjust their process as needs change in their town. |  | Nate Olson
LUE-691 | Land Development | Scheduling Bonds | Assign to plan reviewers As a LD Manager | As a LD Manager I want any revisions to a plan get assigned to the plan reviewers even if the LD manager performed the plan review. So that the plan reviewers are assigned to complete the work. |  | Nate Olson
LUE-741 | Land Development | Scheduling Bonds | Checklist for plat reviewAs a plat reviewer | As a plat reviewer I want to complete a checklist of items to review while performing the plat review So that I can make sure I complete all the reviewed items. |  | Nate Olson
LUE-747 | Land Development | Scheduling Bonds | Apply signature to signed and sealed platAs a plat reviewer | As a plat reviewer I want to digitially sign the signed and sealed plat So that it can be included in the recorded copy |  | Nate Olson
LUE-749 | Land Development | Scheduling Bonds | Route to additional person for signature approvalAs a town | As a town I want to be able to route to others systemically for approval So that they can apply their signature approval to the plat |  | Nate Olson
LUE-767 | Land Development | Plan Review | Categorize MarkupAs a customer | As a customer I want system to categorize each markup on the plan based on how the sheets were categorized So that the customer knows where problems exist. |  | Nate Olson
LUE-768 | Land Development | Plan Review | List of issues per cycleAs a customer | As a customer I want to view a list of issues associated with each plan review cycle So that I can see a summary of all the issues at one time. |  | Nate Olson
LUE-773 | Land Development | Plan Review | Extract marked up plansAs a customer | As a customer I want to be able to extract the marked up plans from the system. So that I can save them to my personal computer. |  | Nate Olson
LUE-783 | Land Development | Plan Review | Markup PlansAs a Plan Reviewer | As a Plan Reviewer I want to mark up a set of plans So that I can show the customer where issues exist and corrections need o be made |  | Nate Olson
LUE-796 | Land Development | Plan Review | Communicate questionsAs a Plan Reviewer | As a Plan Reviewer I want to be able to communicate questions to the customer on the application from the system. So that we can get the information we need to complete the review |  | Nate Olson
LUE-806 | Land Development | Plan Review | Multiple sheet disposition As a Plan reviewer | As a Plan reviewer I want to be able to disposition multiple sheets at the same time So that I can perform the action in a more efficient matter |  | Nate Olson
LUE-810 | Land Development | Plan Review | Live reviewAs a plan reviewer | As a plan reviewer I want to perform a live review feature So that the customer can see the plans as I mark them up |  | Nate Olson
| Code Enforcement | Customer Access | Account Creation As a CE Customer | As a CE Customer I want the ability to create an online account So that I can establish an account for my company |  | Sara Fisher
| Code Enforcement | Customer Access | Add User Profiles As a CE Customer | As a CE Customer I want the ability to add User profiles to my account So that add additional users and manage user profiles |  | Sara Fisher
| Code Enforcement | Customer Access | Create Customer Roles As a CE Business System Admin | As a CE Business System Admin I want the ability to create Customer Roles So that I can manage CE Customer Roles and User Access rights |  | Sara Fisher
| Code Enforcement | Designer | Meck ID As a CE Designer | As a CE Designer I want the abiltiy to create a Meck ID So that I have the ability to submit projects as a designer |  | Sara Fisher
| Code Enforcement | Customer Access | Contractor Auto Credential As a CE Contractor | As a CE Contractor I want my WebPermit/Outrider account to automatically credential me into Accela when submitting a Plan Review required application So that I do not have multiple logins for each system |  | Sara Fisher
| Code Enforcement | Customer Access | Homeowner Auto Credential As a CE Homeowner | As a CE Homeowner I want my WebPermit/Outrider account to automatically credential me into Accela when submitting a Plan Review required application So that I do not have multiple logins for each system |  | Sara Fisher
| Code Enforcement | Estimation | GAP Communicate questionsAs a Estimator | As a Estimator I want to be able to communicate questions to the customer on the application from the system. So that I can clarify necessary details on the application. |  | Sara Fisher
| Code Enforcement | Estimation | Agency Estimation As an Trade Estimator | As an Estimator I want to indicate how many hours each trade review is going to take to complete. So that we can plan the duration of the review. |  | Sara Fisher
| Code Enforcement | Estimation | Answer questionsAs a CE Customer | As a CE Customer I want to be able to answer questions the Estimator has on the application from the system. So that I can be notified and respond |  | Sara Fisher
| Code Enforcement | Estimation | Assign multiple plan reviewers by tradeAs a Estimator | As a Estimator I want to select a secondary choice for who will complete the plan review So that the system has a second choice in planning to schedule the plan reviewere |  | Sara Fisher
| Code Enforcement | Estimation | Assign plan reviewers by tradeAs a Estimator | As a Estimator I want to be able to assign the primary plan reviewers for the project So that they can complete the plan review |  | Sara Fisher
| Code Enforcement | Estimation | Change assigned coordinatorAs a coordinator | As a coordinator I want to be able to change the assigned coordinator for a project. So that it can be adjusted as necessary. |  | Sara Fisher
| Code Enforcement | Estimation | Change assigned coordinatorAs a Estimator | As a Estimator I want to be able to change the assigned coordinator for a project. So that it can be adjusted as necessary. |  | Sara Fisher
| Code Enforcement | Estimation | City fire agency is estimated by code enforcementAs a Estimator | As a Estimator I want City Fire agency projects to be reviewed by a code enforcement estimator and not the agency. So that this is completed by code enforcement. |  | Sara Fisher
| Code Enforcement | Estimation | Complete Estimation As an Agency | As an Agency I want to be able to complete estimation for a project So that the project can be estimated for my agency. |  | Sara Fisher
| Code Enforcement | Estimation | County fire estimation As a County Fire Agency | As a County Fire Agency I want to perform estimation for County fire projects So that we can estimate it. |  | Sara Fisher
| Code Enforcement | Estimation | County shop drawings defaultAs a County Fire Estimator | As a Estimator I want City shop drawings to default to a 1 hours So that I don't have to manually enter a time. |  | Sara Fisher
| Code Enforcement | Estimation | Edit estimated hours As a Estimator | As a Estimator I want to be able to edit the estimated review hours So that we can adjust as needed |  | Sara Fisher
| Code Enforcement | Estimation | Estimate re-review timeAs a plan reviewer | As a plan reviewer I want to enter estimated hours for rereview after rejecting a cycle So that this time will be used for future cycles estimation |  | Sara Fisher
| Code Enforcement | Estimation | Estimation for townhomes. As a Townhome Estimator | As a Estimator I want only want to perform estimation for RTAC projects for townhomes. So that we can estimate only projects that need it. |  | Sara Fisher
| Code Enforcement | Estimation | Estimation is not applicable As an estimator | As an estimator I want to be able to mark estimation as not applicable at each trade level So that estimation will not be completed for that item |  | Sara Fisher
| Code Enforcement | Estimation | Exclude a trade from review As an Estimator | As an Estimator I want to be able to exclude a trade from review. So that review is not necessary for that trade. |  | Sara Fisher
| Code Enforcement | Estimation | Exclude plan reviewers by tradeAs a Estimator | As a Estimator I want to be able to indicate who will not be a plan reviewer for the project So that they will not be assigned as a plan review |  | Sara Fisher
| Code Enforcement | Estimation | GAP Information for estimationAs a Estimator | As a Estimator I want access to key project information. So that I can provide better estimation. |  | Sara Fisher
| Code Enforcement | Estimation | Hours for each trade review As an Estimator | As an Estimator I want to indicate how many hours each trade review is going to take to complete. So that we can plan the duration of the review. |  | Sara Fisher
| Code Enforcement | Estimation | Remove dept or agency from reviewAs an Estimator | As an Estimator I want to be able to remove the department or agency from review So that they do not have to complete the review. |  | Sara Fisher
| Code Enforcement | Estimation | Route to coordinator As a Estimator | As a Estimator I want the project to be routed to the Coordinator once the project has been estimated So that the coordinator can work on scheduling |  | Sara Fisher
| Code Enforcement | Estimation | Set Default Plan Review timeAs a Estimator | As a Estimator I want City Fire agency projects to default to a 1.5 hours So that I don't have to manually enter a time. |  | Sara Fisher
| Code Enforcement | Estimation | System assigns plan reviewerAs a Estimator | As a Estimator I want the system to choose between the primary and secondary plan reviewer I selected and assign the plan review to one of them. So that the plan reviewer will be assigned by the system per business rules. |  | Sara Fisher
| Code Enforcement | Scheduling | SchedulingAs a Business System Admin | As a Business System Admin I want a ability to create business rules for Scheduling Plan Review projects during specific work hours So that plan review projects are scheduled within specific business hours |  | Sara Fisher
| Code Enforcement | Scheduling | SchedulingAs a Business System Admin | As a Business System Admin I want a ability to create business rules for specific scheduling rules So that project hours are scheduled consecutively based on time estimated for scheduling |  | Sara Fisher
| Code Enforcement | Scheduling | User Profiles for SchedulingAs a Business System Admin | As a Business System Admin I want a ability to create business rules for specific user profiles for scheduling So that spedific plan review projects are assigned to plan reviewers based on profiles |  | Sara Fisher
| Code Enforcement | Scheduling | Meeting Types - SchedulingAs a Business System Admin | As a Business System Admin I want a ability to create business rules for specific meeting types for scheduling So that specific meeting types can be scheduled based on business rules |  | Sara Fisher
| Code Enforcement | Scheduling | Project Types - SchedulingAs a Business System Admin | As a Business System Admin I want a ability to create business rules for specific project types for scheduling So that specific project types can be scheduled based on business rules |  | Sara Fisher
| Code Enforcement | Scheduling | Non-Project Appointment SchedulingAs a Business System Admin | As a Business System Admin I want a ability to create business rules for scheduling specific non-Project Appointments So that users based on user role can schedule specific Non-Project Appointments to a plan reviewer |  | Sara Fisher
| Code Enforcement | Scheduling | Express Review SchedulingAs a Business System Admin | As a Business System Admin I want a ability to create business rules for pre-scheduling Express Review hours So that the Express Facilitator can pre-schedule Plan Reviewers for Express Review dates |  | Sara Fisher
| Code Enforcement | Scheduling | Express Review SchedulingAs a Express Plan Review Facilitator | As a Express Plan Review Facilitator I want the ability to manually schedule Plan Reviewer's within the Prescheduled Express Review time, when approved by management So that the Express Facilitator can pre-schedule Plan Reviewers for Express Review dates |  | Sara Fisher
| Code Enforcement | Scheduling | Non-Project Appointment SchedulingAs a Plan Review Facilitator | As a Plan Review Facilitator I want the ability to cancel Non Project Appointments from Plan Reviewer's schedule, when approved by management So that I can cancel Non Project Appointments when approved by management or booked in error |  | Sara Fisher
| Code Enforcement | Scheduling | Non-Project Appointment SchedulingAs a Plan Review Facilitator | As a Plan Review Facilitator I want the ability to schedule mulitple plan reviewers when scheduling Non Project Appointments So that I can efficiently schedule multiple plan reviewers for Non Project appointments |  | Sara Fisher
| Code Enforcement | Scheduling | Manual SchedulingAs a Plan Review Facilitator | As a Plan Review Facilitator I want the ability to manually schedule Plan Review Project hours So that I can schedule Plan Review hours manually when applicable |  | Sara Fisher
| Code Enforcement | Scheduling | Self-SchedulingAs a CE Customer | As a CE Customer I want the ability to Self Schedule the first plan review cycle So that I can schedule the first plan review cycle |  | Sara Fisher
| Code Enforcement | Scheduling | NotificationAs a CE Customer | As a CE Customer I want to receive notification when the Plan Review Facilitator has scheduled my project or meeting So that I can Accept or Reject the scheduled dates |  | Sara Fisher
| Code Enforcement | Scheduling | Acceptance/Rejection PR HoursAs a CE Customer | As a CE Customer I want the ability to enter a new Plans Ready Date when I reject the scheduled Plan Review Dates So that I can provide a new Plans Ready Date for scheduling |  | Sara Fisher
| Code Enforcement | Scheduling | Self-SchedulingAs a Business System Admin | As a Business System Admin I want the Self-Scheduling tool to assign plan reviewers based on the Load Balancing Rules So that the scheduling tool uses load balancing when scheduling the plan review |  | Sara Fisher
| Code Enforcement | Scheduling | Self-SchedulingAs a Business System Admin | As a Business System Admin I want the Self-Scheduling tool to assign the same plan reviewers used in previous plan review cycles So that the scheduling tool assigns previous plan reviewers |  | Sara Fisher
| Code Enforcement | Scheduling | Self-SchedulingAs a Business System Admin | As a Business System Admin I want the Self-Scheduling tool to assign plan review who have been requested by the CE Estimator So that the scheduling tool assigns requested plan reviewers |  | Sara Fisher
| Code Enforcement | Scheduling | Self-SchedulingAs a Business System Admin | As a Business System Admin I want the Self-Scheduling tool to assign plan review to the same plan reviewers who completed a Preliminary Meeting So that the scheduling tool assigns plan reviewers who completed an associated Preliminary Meeting |  | Sara Fisher
| Code Enforcement | Scheduling | Self-SchedulingAs a Business System Admin | As a Business System Admin I want the Self-Scheduling tool to recognize specific plan review teams based on the application type submitted So that the scheduling tool assigns plan reviewers based on teams |  | Sara Fisher
| Code Enforcement | Scheduling | Pre-populate ReviewersAs a Plan Review Facilitator | As a Plan Review Facilitator I want the designated Plan Reviewer to pre-populate when scheduling the project So that the pre-designated Plan Reviewer requested by the Estimator is pre-populated during Auto Scheduling |  | Sara Fisher
| Code Enforcement | Scheduling | Auto-SchedulingAs a Plan Review Facilitator | As a Plan Review Facilitator I want the ability to select Auto-Scheduling to schedule plan review hours So that I can easily schedule plan review hours for a project |  | Sara Fisher
| Code Enforcement | Scheduling | As a Business System Admin | As a Business System Admin I want the ability to configure Holiday Hours So that I can projects will not be scheduled on these dates |  | Sara Fisher
| Code Enforcement | Scheduling | Auto-Update Gate DateAs a Plan Review Facilitator | As a Plan Review Facilitator I want the Gate Date to automatically update when a Plan Review has been re-scheduled manually So that the correct Gate Date is maintained in the system |  | Sara Fisher
| Code Enforcement | Scheduling | NotificationAs a CE Customer | As a CE Customer I want to receive notification when my project Gate Date has been changed due to manaul scheduling So that I receive email and dashboard notification when the Gate Date has been changed due to manual scheduling |  | Sara Fisher
| Code Enforcement | Scheduling | N/A Scheduling As a Business System Admin | As a Business System Admin I want to create business rules for scheduling when the original trade is Not Applicable during Estimation but needs to be scheduled in a subsequent plan review cycle So that when drawings are submitted for a trade which was Not Applicable in a subsequent plan review cycle the PR Facilitator can schedule the trade reviewer |  | Sara Fisher
| Code Enforcement | Scheduling | Scheduling when PR is completed early As a Business System Admin | As a Business System Admin I want to create business rules for scheduling when a Plan Reviewer completes their project review prior to the scheduled plan review date So that upon completion of the plan review the plan review hours are removed from their calendar and open for additional project hours |  | Sara Fisher
| Code Enforcement | Scheduling | Scheduling Trades separatelyAs a Business System Admin | As a Business System Admin I want to create business rules for scheduling all trades separately during the scheduling process So that all trades are scheduled separately based on business rules |  | Sara Fisher
| Code Enforcement | Scheduling | A/E Superior PerformersAs a Business System Admin | As a Business System Admin I want to create business rules Superior Performing A/E based on Pass/Fail Performance Rating So that Superior Performing Team projects are scheduled first during the Auto Scheduling process |  | Sara Fisher
| Code Enforcement | Scheduling | 2nd Cycle Scheduling Large Projects As a Business System Admin | As a Business System Admin I want to create business rules for scheduling 2nd Cycle Plan Reviews for large projects, when applicable So that the Plan Review Facilitator can schedule the 2nd cycle review prior to the completion of the first plan review cycle |  | Sara Fisher
| Code Enforcement | Scheduling | Pre-populate ReviewersAs a Business System Admin | As a Business System Admin I want to create business rules to pre-populate Plan Reviewers names when Preliminary Meeting is checked on the application So that the Plan Review Facilitator can schedule the plan review hours to the same meeting attendees |  | Sara Fisher
| Code Enforcement | Scheduling | Pre-populate ReviewersAs a Business System Admin | As a Business System Admin I want to create business rules to pre-populate Plan Reviewers names when Revision to Approved Plan is submitted and the original project number is provided So that the Plan Review Facilitator can schedule the plan review hours to the original plan reviewers |  | Sara Fisher
| Code Enforcement | Scheduling | Acceptance/Rejection PR HoursAs a Business System Admin | As a Business System Admin I want to create business rules for customer acceptance or rejection of the scheduled plan review hours So that the customer has a designated time to Accept/Reject the plan review hours or they will be automatically removed |  | Sara Fisher
| Code Enforcement | Scheduling | Manual SchedulingAs a Business System Admin | As a Business System Admin I want to create business rules for manually scheduling project hours on the next business day, when applicable So that the Plan Review Facilitator can manually schedule a plan review on the next business day, when applicable |  | Sara Fisher
| Code Enforcement | Scheduling | Express Review SchedulingAs a CE Plan Review Facilitator | As a CE Plan Review Facilitator I want to Express Plan Review projects to be scheduled on specific dates and times So that I can manage Express Plan Review scheduling |  | Sara Fisher
| Code Enforcement | Scheduling | NotificationAs a CE Plan Review Facilitator | As a CE Plan Review Facilitator I want to Express Plan Review email notification to customer to contain Express Review Fee calculations So that I customer receives the Express Plan Reviews due prior to the review date |  | Sara Fisher
| Code Enforcement | Scheduling | Express Review SchedulingAs a CE Customer | As a CE Customer I want to the ability to request my subsequent plan review Cycle for a project to be scheduled as an Express Plan Review So that I request Express review schedule for my subsequent cycle |  | Sara Fisher
| Code Enforcement | Scheduling | NotificationAs a CE Express Plan Review Facilitator | As a CE Express Plan Review Facilitator I want to to receive email notifications that Express Plan Review has been requested for a non-Express Review application So that I upon Management approval, I can schedule the subsequent plan review cycle as Express Review |  | Sara Fisher
| Code Enforcement | Scheduling | RTAP SchedulingAs a CE Plan Review Facilitator | As a CE Plan Review Facilitator I want Revision to Approved Plans project applications to be assigned to the original plan review team So that the Plan Reviewers from the original plan review project are assigned to the RTAP review |  | Sara Fisher
| Code Enforcement | Scheduling | MMF SchedulingAs a CE Mega Multi Family Plan Review Facilitator | As a CE Mega Multi Family Plan Review Facilitator I want applications submitted for MMF projects to be auto-assigned to the MMF team during scheduling So that when I perform scheduling the MMF team is assigned the project |  | Sara Fisher
| Code Enforcement | Scheduling | SPT SchedulingAs a CE Special Projects Team Plan Review Facilitator | As a CE Special Projects Team Plan Review Facilitator I want applications submitted for SPT projects to be auto-assigned to the SPT team during scheduling So that when I perform scheduling the SPT team is assigned the project |  | Sara Fisher
| Code Enforcement | Meetings | Dashboard, Meeting ConfigurationAs a CE Customer | As a CE Customer I want the ability to submit Project Meeting requests So that I can request meetings within the Plan Review Project dashboard |  | Sara Fisher
| Code Enforcement | Meetings | Dashboard, Meeting ConfigurationAs a CE Customer | As a CE Customer I want to receive Dashboard Notifications for requested meeting types when scheduled So that I Accept or Reject the Scheduled Date or Request a New Meeting Date |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a CE Plan Reviewer | As a CE Plan Reviewer I want the to receive Dashboard Notiications when a customer requests a Single Trade Meeting So that I can manage and facilitate the Single Trade Exit Meeting |  | Sara Fisher
| Code Enforcement | Meetings | NotificationAs a CE Plan Review Facilitator | As a CE Plan Review Facilitator I want the to receive Dashboard Notiications when a customer requests a specific Meeting Types So that I can schedule and facilitate the meetings |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an Exit Meeting So that I can create and/or modify Business Rules for as needed |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a CE Plans Reviewer | As a CE Plans Reviewer I want the abiity to request an Exit Meeting So that I can manage an Single Trade - Exit Meeting through my Project Dashboard |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a CE Plans Reviewer | As a CE Plans Reviewer I want the abiity to request an Exit Meeting So that I can manage an Multi Trade - Exit Meeting through my Project Dashboard |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a CE Plan Reviewer | As a CE Plan Reviewer I want the the ability to Accept or Reject a Exit Meeting So that I can determine if I need to attend a Single Trade Exit Meeting I have been added to |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a CE Plan Reviewer | As a CE Plan Reviewer I want the the ability to Accept or Reject a Exit Meeting So that I can determine if I need to attend a Multi Trade Exit Meeting I have been added to |  | Sara Fisher
| Code Enforcement | Meetings | NotificationAs a CE Plans Review Facilitator | As a CE Plans Review Facilitator I want to receive Dashboard Notifications for an Exit Meeting when requested by the CE Plans Examiner So that I can receive Notifications and schedule accordingly |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for a Collaborative Meeting So that I can create and/or modify Business Rules for as needed |  | Sara Fisher
| Code Enforcement | Meetings | NotificationAs a CE Plan Reviewer | As a CE Plan Reviewer I want the abiity to receive dashboard notifications for a Collaborative Meeting So that I can view the meetiings on my schedule dashboard |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a CE Plan Reviewer | As a CE Plan Reviewer I want the abiity to request a Collaborative Meeting So that I can schedule and facilitate the meetings |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for a Pre-Permitting Meeting So that I can create and/or modify Business Rules for as needed |  | Sara Fisher
| Code Enforcement | Meetings | NotificationAs a CE Plans Reviewer | As a CE Plans Reviewer I want to received Dashboard notifications when a Pre-Permitting document has been uploaded So that I can Approve or Disapprove the document |  | Sara Fisher
| Code Enforcement | Meetings | NotificationAs a CE Customer | As a CE Customer I want to received Dashboard notifications when a Pre-Permitting document Approved or Disapproved So that I can take necessary action based |  | Sara Fisher
| Code Enforcement | Meetings | Meeting ConfigurationAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for a Phasing Meeting So that I can create and/or modify Business Rules for as needed |  | Sara Fisher
| Code Enforcement | Meetings | NotificationAs a CE Plans Reviewer | As a CE Plans Reviewer I want to received Dashboard notifications when a Phasing document has been uploaded So that I can Approve or Disapprove the document |  | Sara Fisher
| Code Enforcement | Meetings | NotificationAs a CE Customer | As a CE Customer I want to received Dashboard notifications when a Phasing document Approved or Disapproved So that I can take necessary action based |  | Sara Fisher
| Code Enforcement | Meetings | MessagingAs a Business System Admin | As a Business System Admin I want to display an information text box message for each meeting type So that add specific text description for each meeting type |  | Sara Fisher
| Code Enforcement | Plan Review | CE checklistAs a CE plan reviewer | As a CE plan reviewer I want to complete a checklist for each plan review So that I can be sure to check all items as needed |  | Sara Fisher
| Code Enforcement | Plan Review | Plan Review Checklist As a CE plan reviewer | As a CE plan reviewer I want a Plan Review checklist added to my specific trade plan review So that I complete my plan review checklist during my plan review |  | Sara Fisher
| Code Enforcement | Plan Review | Plan Review Checklist As a CE Agency plan reviewer | As a CE Agency plan reviewer I want a Plan Review checklist added to my specific agency plan review So that I complete my plan review checklist during my plan review |  | Sara Fisher
| Code Enforcement | Plan Review | External CustomerAs a External Customer | As a External Customer I want the ability to view Plan Review project notes and details without logging into a system. So that I can view project information from an external customer website |  | Sara Fisher
| Code Enforcement | Plan Review | External Customer As a Business System Admin | As a Business System Admin I want the ability to modify the information provided to the External customer for a project So that I can manage the project information displayed on external customer website |  | Sara Fisher
| Code Enforcement | Fees | Estimated FeesAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an Estimated Permit/Plan Review Fees (Upfront fees) So that I can create and/or modify Business Rules for as needed |  | Sara Fisher
| Code Enforcement | Fees | Bond ValidationAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an Bond Account Validation So that I can create and/or modify Business Rules for as needed |  | Sara Fisher
| Code Enforcement | Fees | Fee Estimator WeblinkAs a CE Customer | As a CE Customer I want the Permit Fee Estimate link displayed in my CE Customer Dashboard So that I can calculate estimated Permit Fees for my project permits |  | Sara Fisher
| Code Enforcement | Fees | Data Entry Plan Review FeesAs a CE Plan Review Agency | As a CE Plan Review Agency I want the to enter my Plan Review Fees during my Plan Review So that I can key applicable Plan Review Fees |  | Sara Fisher
| Code Enforcement | Fees | Data Entry Plan Review FeesAs a CE City Zoning Plan Reviewer | As a CE City Zoning Plan Reviewer I want the ability to enter my RTAP Plan Review fee So that I can enter my fees upon completion of my RTAP plan review |  | Sara Fisher
| Code Enforcement | Fees | Estimated vs ActualAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an Estimated and Actual Plan Review fees for projects with a construction cost equal to or greater than $1,000,000 So that I can display Estimated and Actual Plan Review fees |  | Sara Fisher
| Code Enforcement | Fees | Estimated vs ActualAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an Estimated and Actual Plan Review fees for RTAP (Revision to Approved Plans) So that I can display Estimated and Actual Plan Review fees for chargeable RTAP reviews |  | Sara Fisher
| Code Enforcement | Fees | Estimated vs ActualAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an Estimated and Actual Plan Review fees for projects with a construction cost less than $1,000,000 and are not MMF or SPT So that I can display Estimated and Actual Plan Review fees |  | Sara Fisher
| Code Enforcement | Fees | Estimated vs ActualAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an Estimated and Actual Plan Review fees when Project/Application Type is MMF or SPT So that I can display Estimated and Actual Plan Review fees |  | Sara Fisher
| Code Enforcement | Fees | Fee ConfigurationAs a Business System Admin | As a Business System Admin I want the abiity to create Business Rules for an projects with a construction cost less than $1,000,000, are not MMF or SPT, and had a successful Preliminary Meeting So that I can display applicable message regarding fees |  | Sara Fisher
| Code Enforcement | Fees | Actual Plan Review FeesAs a CE Plan Review Facilitator | As a CE Plan Review Facilitator I want the Actual Plan Review fees for all project types to be displayed in my project dashboard So that I can manage and facilitate the charging of fees in Winchester |  | Sara Fisher
| Code Enforcement | Fees | Fee ScheduleAs a CE Manager | As a CE Manager I want the ability to update the Fee Schedule So that I can update the specific fees as needed |  | Sara Fisher
| Code Enforcement | Fees | PaymentAs a CE Customer | As a CE Customer I want the ability to pay my Estimated Permit/Plan Review (Upfront) fees within my project So that I can pay my fees through my project |  | Sara Fisher
| Code Enforcement | Fees | Abort/Cancellation FeesAs a CE Customer | As a CE Customer I want the ability to pay my Abort/Cancellation fees within my project So that I can pay my fees through my project |  | Sara Fisher
| Code Enforcement | Close Out | NotificationAs a CE Customer | As a CE Customer I want to receive a email notification when a project has closed So that I receive a detailed notification of required information to issue the permit/s |  | Sara Fisher
| Code Enforcement | Close Out | Close Out FeesAs a Business System Admin | As a Business System Admin I want the system to automatically calculate plan review fees, if applicable So that when the CE Customer receives the email/dashboard notification applicable plan review fees are included |  | Sara Fisher